## Sheet1
Task | Task description | LOE |  |  |  | Notes
|  | Chris | Luke | Mike | Paula
TOTAL LOE, Baseline Tool |  | 72 | 72 | 56 | 56
TOTAL LOE, Baseline Tool + GUI |  | 78 | 78 | 92 | 56
TOTAL LOE, Baseline Tool + GUI + Cloud |  | 82 | 82 | 124 | 56
Ongoing maintenance (DMG or Health staff with training) |  | 10~15 hours / month
1 | Media analysis
1.1 | Identify media outlets | 4 |  |  |  | Not all media outlets have public APIs for content extraction, thus we may need to build web scrapers from scratch, and tailor the web scrapers to different media website designs. Text analytics for long texts (articles) can be more sophisticated than for short ones (e.g. tweets). A third party service such as Google Cloud text analytics may be used at a small cost (e.g. we previously processed 12,000+ government rule comments at $27).
· Health oriented, e.g. Modern Healthcare, Medscape
· Law firms / lobbying groups, e.g. Ropes & Gray, Baker Donelson
· Watchdog / advocacy sites, e.g. Pro Poblica, AARP
· Peer-reviewed literature, e.g. JAMA
1.2 | Build automation tool to extract text data from media outlets, output as structured files (e.g. csv) | 16
· API-based text data query
· Build web scraper to extract unstructured data, and organize
· Meta-data collection, e.g. date of publishing, geographic area of interest
1.3 | Meta-data analysis | 16
· Arrival rate / incidence rate analysis (temporal)
· Geographic coverage analysis (spatial)
1.4 | Machine learning based text analysis | 32
· Sentiment analysis - estimate distribution of negative/neural/positive sentiments embedded in text
· Topic modeling - identify key words and topics in articles
2 | Social media analysis
2.1 | Build automation tool to extract social media contents, e.g. using Twitter API to extract tweets and generate structured data such as csv (timestamp/geographic origin/text content/relationship to CMMI tweets) |  | 16 |  | 8 | A unique feature of social media analysis is the measurability of influence of messages, e.g. retweet counts of a CMMI tweet. Influence can be analyzed over time (using tweet timestamps) and across areas (using geolocation meta-data in extracted JSON files using Twitter API).
2.2 | Meta-data analysis |  | 16 |  | 8
· Arrival rate analysis (temporal)
· Geographic coverage analysis (spatial)
· Analysis of engagement with CMMI tweets (e.g. retweet status)
2.3 | Machine learning based text analysis |  | 32
Sentiment analysis - estimate distribution of negative/neural/positive sentiments embedded in tweets
Topic modeling - identify key words and topics in tweets
Entity identification - identify stakeholders mentioned especially in ‘sales pitch’ tweets.
3 | Google Trend analysis
3.1 | Develop set of phrases of interest based on |  |  | 4 |  | Google Trend does not have a public API, so query tool would either be (i) unofficial library such as google-trends-api or (ii) a web-scraper scrpited from scratch
· CMMI announcements
· Model keywords
· New phrases arising from media/social media
customized to availability of Google Trend data
3.2 | Build automation tool to query Google Trend data. Tool should produce temporal search intensity data based on phrases queried and time interval specified. |  |  | 16
3.3 | Google Trend data analysis |  |  | 12
· Identify any temporal trends
· Identify any spikes in interest in topics
4 | Validation
4.1 | Validation of text analysis results using human labeled data |  |  |  | 8 | Validation using human labeled data informs about validity of the ML algorithms employed. Validation of results from ML algortiths across data sources informs about how topics/sentiments align between content origins (professionals/policy makers/general public)
· Identify a testing set of articles/tweets, and flag topics/sentiments using human eyes
· Cross-validate topics/sentiments flagged by human and by machine, and evaluate results
4.2 | Validation of text analysis results across media sources | 4 | 8 |  | 16
· cross validate topics identified from media and social media
· cross validate sentiment distribution estimated from media and social media texts
· cross validate arrival rate of media and social media responses
· cross validate geographic distribution of origins of media and social media contents
4.3 | Validation against external data sources, e.g. geographic topic distribution comparison against Leapfrog safety measure data |  |  |  | 16
5 | Build an environment to integrate all analytic components
5.1 | Script code to develop an integration environment to enable one-stop tool running. Without a GUI, code will be run from command line. A step-by-step user guide will be developed. |  |  | 24 |  | The integration environment will be needed for any version of the tool for consistent monitoring of multiple media sources. Without GUI, user will need Python installed to run the code.
6 | Graphic User Interface (GUI)
6.1 | Design a GUI to integrate and present all analysis results | 2 | 2 | 4 |  | We recommend a web-based interface for ease of user access, with a user authentication system to ensure security
6.2 | Implement a user-friendly interface which is ported to all back-end analytics in Task 1/2/3/4. | 4 | 4 | 24
6.3 | Runtime testing / testing across different OS / testing of executable compilation |  |  | 8
7 | Cloud-based tool implementation
7.1 | Adapt all code / data sources / project structure to cloud setting | 4 | 4 | 16 |  | Cloud options: AWS/Google Cloud/MS Azure. We have worked mostly with AWS but will explore other options as needed. Estimated cost of cloud service (sever rental) is $100-$200 per month.
7.2 | Cloud-based testing of tool |  |  | 8
7.3 | Set up code for regular automated monitoring |  |  | 8